COUNTY GOVERNMENT OF KIRINYAGA

KERUGOYA/ KUTUS MUNICIPAL BOARD

ANNUAL COUNTY URBAN INSTITUTIONAL DEVELOPMENT PLAN

2017/2018 FY

Office of the Governor 
Kirinyaga County

P.O. Box 260 – 10304

KUTUS, KENYA

- INTRODUCTION

The Annual Municipal Investment Development plan (IDeP budget) has been prepared pursuant to provision of Urban Areas and Cities Act (UACA 2011) and in compliance with the KUSP Program Operation Manual (POM).

The Plan and Budget outlines the specific project/programmes to be implemented using the World Bank funded conditional grants dubbed Urban Institutional Grant (UIG).

The program/project have been selected from eligible investment priority areas, table 3.2, POM Vol.1.

The plan has been prepared by a task force drawn from key project implementing departments with emphasis on the departments responsible for implementing development projects that fall within the eligible investment priority areas. The task force drew its members from specific directorates including: Economic Planning, Lands, Housing, Urban Development, Environment, Trade, Cooperatives and Industrialization, and Roads.

The preparation of the plan was anchored on the five-year development plan popularly known “County Integrated Development plan, 2018-2022”. Preparation of the CIDP was a consultative process that intensely involved multiple public participation fora in line with provisions of Section 87 of the County Governments Act. During preparation of CIDP 2018-2022, Members of the public were given a platform through which they presented and prioritized the projects and programs to be implemented within the five-year period.

The Municipal Investment Plan is an extract of the CIDP taking into consideration the eligible investment priority areas as enshrined in the Project Operations Manual of the Urban Support Program.

- CONTEXT

County Urban Institutional Development Plan identifies five main objectives and clearly defines the strategy to be applied in order to achieve the objectives.

| No. | Objective | Strategy for Achieving the Objective |
| --- | --- | --- |
| 1. | To Update Local Physical Development Plans | The County Government has allocated resources in the main stream budget for the update of development Plans for select Urban Areas in the County. |
| 2. | To Prepare Custom Development Plan and Zoning Guidelines | Review/ Obtain current population in major Urban Areas. Fast track the Completion of the Mountain Cities Blueprint which shall form the basis of Planning. Undertake fresh Zoning based on the County Mountain Cities Blueprint 2032. |
| 3. | To provide basic Infrastructure, basic Services and Utilization | Allocate the UDG grants with an aim of giving the much-needed Infrastructure, Services and Utilization in the Kerugoya – Kutus Municipality. |
| 4. | Establish Kerugoya/ Kutus Municipality, Institutionalize Municipal Board and Fill the Municipal Manager position. | The County Government of Kirinyaga has advertised for the position of Kerugoya/ kutus Municipal Manager. The County Government has developed the duties/ functions of the Municipal Manager. The County Government has advertised with an aim of filling the vacant Municipal Board Position. |
| 5. | To develop Annual Action Plan and Budget | The County Government has developed the Action Plan for the institutionalization of the Municipality and has since prepared the budget estimates for inclusion in the 2017/18 financial Year Budget. |

The Initial plan provided for in the strategy of achieving objectives with its budget capped at Ksh. twenty million for FY 2017/2018 as provided in the County Allocation of Revenue Act 2017.

- URBAN INVESTMENT PLAN AND BUDGET FY 2017/ 2018

UIG Budget FY 2017/ 2018

The total available budget is Ksh 20,000,000 having met the minimum conditions. The funds will be used to facilitate creation of institutional frameworks to absorb the grant in Window 3.

| Table 1: Municipal Investment Budget 2017/2018-UIG |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Timeframe |  | Budget |  |  |  |
| No | Activity | Responsible party for implementation | Start date | End date | UIG | County Mainstream Budget | Other-2 | Total |
| 1. | Preparation of Kerugoya/Kutus Urban Plan | Chief officer- Urban development | 1st July 2017 | 30th June 2018 | 12,500,000 | - |  | 12,500,000 |
| 2. | Establish Kerugoya/Kutus Municipal office | Chief officer- Urban development | 1st July 2017 | 30th June 2018 | 7,500,000 |  |  | 7,500,000 |
|  |  | TOTAL |  |  | 20,000,000 |  |  | 20,000,000 |

| Table 2: Municipal Investment Budget FY 2017/2018– UIG |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Activity | Timeframe |  |  |  |  |  |  |  |  |  |  |  |
|  |  | J | A | S | O | N | D | J | F | M | A | M | J |
| 1 | Purchase of Furniture and Stationery |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Office |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Orientation for municipal board and municipal manager |  |  |  |  |  |  |  |  |  |  |  |  |

- EXPECTED OUTCOME

The priorities for the 2017/2018 Financial Year as mentioned in the CUIDS will be Preparation of the Kerugoya /Kutus Urban Plan and setting up the office of the Municipal Manager

| Priority/ Rank (No.) | Project name | Activity | Expected Outcome |
| --- | --- | --- | --- |
| 1 | Preparation of Kerugoya/ Kutus Urban Plan | Inception report Basemap preparation Visioning Data Collection Data Analysis 1st Draft Plan Final Plan | Sustainable urban development |
| 2 | Establish Kerugoya/Kutus Municipal office | Administration Orientation and capacity building of the Municipal Board and the Manager | Good working environment |

- IMPLEMENTATION MODALITIES

The Urban board will have core personnel in Finance so that will be answerable directly to the municipal manager. The Municipal Manager will be responsible for implementation of the proposed activities, will manage the budget (requisition officer) and expenditure (authorizing officer).

The Urban boards will be at an ‘arms-length’ from the county structure but performing for the county in its responsibilities for urban management.